## Gantt_Planned
Date | 2017-10-10 | 2017-10-17 | 2017-10-24 | 2017-10-31 | 2017-11-07 | 2017-11-14 | 2017-11-21 | 2017-11-28 | 2017-12-05 | 2017-12-12 | 2017-12-19 | 2017-12-26 | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | TASK TOTAL | SUB TOTAL
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 |  | Contingency | Responsible | Contributor1 | Contributor2
Workload | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 1056 | 144 | project.manager@university.org | MarketingToBeNamed@university.org
Project Management | [23 empty] | 114 | project.manager@university.org | MarketingToBeNamed@university.org
Initiation | 16 | 4 | [20 empty] | 20 |  | project.manager@university.org | MarketingToBeNamed@university.org
Planning | 16 | 12 | 12 | 12 | [18 empty] | 52 |  | project.manager@university.org | MarketingToBeNamed@university.org
Monitoring | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 42 |  | project.manager@university.org | MarketingToBeNamed@university.org
Market Analysis |  | 16 | 8 | [19 empty] | 24 | 96 | project.manager@university.org | MarketingToBeNamed@university.org
Competitor analysis |  |  | 4 | 12 | [18 empty] | 16 |  | project.manager@university.org | MarketingToBeNamed@university.org
Customer analysis |  |  |  |  | 8 | 8 | [16 empty] | 16 |  | project.manager@university.org | MarketingToBeNamed@university.org
Supplier analysis |  |  |  |  | 8 | 8 | [16 empty] | 16 |  | project.manager@university.org | MarketingToBeNamed@university.org
Present Concept | [6 empty] | 24 | [15 empty] | 24 |  | project.manager@university.org | MarketingToBeNamed@university.org
Harware development |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 28 | 326 | designer.engineer@university.org | project.manager@university.org
Design Case |  |  |  |  | 16 | 16 | 8 | [15 empty] | 40 |  | designer.engineer@university.org | project.manager@university.org | manufacturing.engineer@university.org
Print Prototype Case | [7 empty] | 16 | 16 | [13 empty] | 32 |  | designer.engineer@university.org | project.manager@university.org | manufacturing.engineer@university.org
Review Design | [9 empty] | 16 | 16 | [11 empty] | 32 |  | designer.engineer@university.org | project.manager@university.org | manufacturing.engineer@university.org
Research Manufacturing Options | [7 empty] | 14 | 14 | 14 | 14 | 14 | [10 empty] | 70 |  | designer.engineer@university.org | project.manager@university.org | manufacturing.engineer@university.org
Research Power Supply | [11 empty] | 8 | [10 empty] | 8 |  | designer.engineer@university.org | project.manager@university.org | manufacturing.engineer@university.org
Select Power Supply | [12 empty] | 8 | [9 empty] | 8 |  | designer.engineer@university.org | project.manager@university.org | manufacturing.engineer@university.org
Research Power Button | [12 empty] | 8 | [9 empty] | 8 |  | designer.engineer@university.org | project.manager@university.org | manufacturing.engineer@university.org
Select Power Button | [13 empty] | 8 | [8 empty] | 8 |  | designer.engineer@university.org | project.manager@university.org | manufacturing.engineer@university.org
Research Volume Button | [12 empty] | 8 | [9 empty] | 8 |  | designer.engineer@university.org | project.manager@university.org | manufacturing.engineer@university.org
Select Volume Button | [13 empty] | 8 | [8 empty] | 8 |  | designer.engineer@university.org | project.manager@university.org | manufacturing.engineer@university.org
Research Loudspeaker | [13 empty] | 10 | [8 empty] | 10 |  | designer.engineer@university.org | project.manager@university.org | manufacturing.engineer@university.org
Select Loudspeaker | [14 empty] | 10 | [7 empty] | 10 |  | designer.engineer@university.org | project.manager@university.org | manufacturing.engineer@university.org
Design Internal Connectors | [14 empty] | 16 | 8 | [6 empty] | 24 |  | designer.engineer@university.org | project.manager@university.org | manufacturing.engineer@university.org
Case Durability / FEA | [15 empty] | 8 | 8 | 16 |  |  |  |  | 32 |  | designer.engineer@university.org | project.manager@university.org | manufacturing.engineer@university.org
Software Development | 6 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [5 empty] | 42 | 278 | programmer.engineer@university.org | electronics.engineer@university.org | project.manager@university.org
Research Software Plattforms |  |  | 12 | 12 | [18 empty] | 24 |  | programmer.engineer@university.org | electronics.engineer@university.org | project.manager@university.org
Research Raspberry Pi Alternatives |  |  |  |  | 2 | 2 | 2 | [15 empty] | 6 |  | programmer.engineer@university.org | electronics.engineer@university.org | project.manager@university.org
Develop Connection Scenarios | [7 empty] | 4 | 4 | 4 | [12 empty] | 12 |  | programmer.engineer@university.org | electronics.engineer@university.org | project.manager@university.org
Develop Use Cases | [10 empty] | 4 | 12 | 10 | [9 empty] | 26 |  | programmer.engineer@university.org | electronics.engineer@university.org | project.manager@university.org
Evaluate App Options | [13 empty] | 8 | 8 | 8 | 8 | [5 empty] | 32 |  | programmer.engineer@university.org | electronics.engineer@university.org | project.manager@university.org
Raspberri Pi - OS familarisation | 8 | 8 | [20 empty] | 16 |  | programmer.engineer@university.org | electronics.engineer@university.org | project.manager@university.org
Raspberri Pi - IO Interfaces |  |  | 8 | 8 | 8 | [17 empty] | 24 |  | programmer.engineer@university.org | electronics.engineer@university.org | project.manager@university.org
Raspberri Pi - Networking | [5 empty] | 8 | 8 | 8 | [14 empty] | 24 |  | programmer.engineer@university.org | electronics.engineer@university.org | project.manager@university.org
Raspberri Pi - Programming | [8 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [5 empty] | 72 |  | programmer.engineer@university.org | electronics.engineer@university.org | project.manager@university.org
Prototyping and Finalising | [15 empty] | 2 | 2 | 2 | 2 | 2 | 2 |  | 12 | 242 | manufacturing.engineer@university.org | designer.engineer@university.org | software.engineer@university.org
Print and Assemble Prototype | [15 empty] | 8 | 8 | 16 |  |  |  |  | 32 |  | manufacturing.engineer@university.org | designer.engineer@university.org | software.engineer@university.org
Raspberri Pi Prototype Troubleshooting | [16 empty] | 8 | 10 | 8 |  |  |  | 26 |  | manufacturing.engineer@university.org | designer.engineer@university.org | software.engineer@university.org
Manufacturing Cost Analysis | [18 empty] | 16 | 10 |  |  | 26 |  | manufacturing.engineer@university.org | designer.engineer@university.org | software.engineer@university.org
Simulate Assembly Automation | [18 empty] | 16 | 10 |  |  | 26 |  | manufacturing.engineer@university.org | designer.engineer@university.org | software.engineer@university.org
Prepare Presentation | [18 empty] | 4 | 12 | 20 |  | 36 |  | manufacturing.engineer@university.org | designer.engineer@university.org | software.engineer@university.org
Prepare Project Report | [19 empty] | 12 | 24 | 48 | 84 |  | manufacturing.engineer@university.org | designer.engineer@university.org | software.engineer@university.org
[23 empty] | 1056 | 1056

## Contacts
FirstName | FamilyName | Email | Organisation | Phone | Mobile | Address
Oliver | Vogt | oliver.vogt@university.org | EngineeringCompany
Designer | Engineer | designer.engineer@university.org | EngineeringCompany
Programmer | Engineer | programmer.engineer@university.org | EngineeringCompany
Manufacturing | Engineer | manufacturing.engineer@university.org | EngineeringCompany
Director | ToBeNamed | DirectorToBeNamed@university.org | EngineeringCompany
Marketing | ToBeNamed | MarketingToBeNamed@university.org | EngineeringCompany
Finance | ToBeNamed | FinanceToBeNamed@university.org | EngineeringCompany
Bank | ToBeNamed | BankToBeNamed@university.org | Lloyds Bank
S-Customer | standard | S-CustomerToBeNamed@university.org | Rapid Electonics
Adv-Customer | advanced | Adv-CustomerToBeNamed@university.org | Amazon
Retailer | ToBeNamed | RetailerToBeNamed@university.org | Carphone Warehouse
Wholesaler | ToBeNamed | WholesalerToBeNamed@university.org | Amazon
IT-Support | ToBeNamed | IT-SupportToBeNamed@university.org | Waterstone Consultancy
Design | Tutor1 | design.tutor1@university.org | Waterstone Consultancy
Design | Tutor2 | design.tutor2@university.org | Waterstone Consultancy
software | engineer | software.engineer@university.org | EngineeringCompany
electronics | engineer | electronics.engineer@university.org | EngineeringCompany
project | manager | project.manager@university.org | EngineeringCompany
Project | Sponsot | project.sponsor@company.com | Lloyds Bank