## Project_Log
ControllingUID | Activity Type | Activity Name | Activity Description / Comment | Submitted by | Submited Date | Status | Impact on Task | Impact on Budget | Impact on Schedule | Relevant | Reasonable | Risky | Implemented by | Implement Date | Confirmed by | Confirm Date
| Meeting Note | Agenda 10/10 | Goals & Objectives Postit note exercise | project.manager@university.org | 2018-10-11 | Done
| Meeting Note | Agenda 17/10 | Complete project scope | project.manager@university.org | 2018-10-18 | Done
| Meeting Note | Agenda 24/10 | First schedule draft | project.manager@university.org | 2018-10-25 | Done
| Meeting Note | Meeting 01/11 | Meeting: entire team, two project sponsors | project.manager@university.org | 2017-11-01 | Done
| Meeting action | Meeting 01/11 | Revise plan with activities no more than 20% of the total budget | project.manager@university.org | 2017-11-01 | Done | [6 empty] | project.manager@university.org | 2018-11-05 | DirectorToBeNamed@university.org | 2018-11-05
| Meeting action | Meeting 08/11 | Add to select Power button: "Volume +-" and "Prev<>Next" buttons | designer.engineer@university.org | 2017-11-08 | Open | Select Power Button | plus 5 days of work | 5 days delay | Neccessary for swift operation |  | Additional parts to fails?
| Reminder | Invite Pi distributor to the December meeting |  | software.engineer@university.org | 2017-11-10 | Discarded |  |  |  |  | Low purchase volume hence low interest
| Risk review | Monthly risk review Dec | No additional risks to the project | programmer.engineer@university.org | 2017-12-01 | Done
| Scope change | Add touchscreen |  | electronics.engineer@university.org | 2017-12-01 | Discarded | Design Case Internals | + £40 | 4 days delay | Too expensive
| Issue | Raspberry Pi price increase | It is expected that the next version of Raspberry Pi is 100% more expensive | project.manager@university.org | 2017-11-03 | In progress | Market Analysis | none | none |  | Within expectations
| Meeting action | Contact customer | Setup a meeting to discuss the user testing of the prototype | programmer.engineer@university.org | 2018-11-05 | Scheduled

## Contacts
FirstName | FamilyName | Email | Organisation | Phone | Mobile | Address
Oliver | Vogt | oliver.vogt@university.org | EngineeringCompany
Designer | Engineer | designer.engineer@university.org | EngineeringCompany
Programmer | Engineer | programmer.engineer@university.org | EngineeringCompany
Manufacturing | Engineer | manufacturing.engineer@university.org | EngineeringCompany
Director | ToBeNamed | DirectorToBeNamed@university.org | EngineeringCompany
Marketing | ToBeNamed | MarketingToBeNamed@university.org | EngineeringCompany
Finance | ToBeNamed | FinanceToBeNamed@university.org | EngineeringCompany
Bank | ToBeNamed | BankToBeNamed@university.org | Lloyds Bank
S-Customer | standard | S-CustomerToBeNamed@university.org | Rapid Electonics
Adv-Customer | advanced | Adv-CustomerToBeNamed@university.org | Amazon
Retailer | ToBeNamed | RetailerToBeNamed@university.org | Carphone Warehouse
Wholesaler | ToBeNamed | WholesalerToBeNamed@university.org | Amazon
IT-Support | ToBeNamed | IT-SupportToBeNamed@university.org | Waterstone Consultancy
Design | Tutor1 | design.tutor1@university.org | Waterstone Consultancy
Design | Tutor2 | design.tutor2@university.org | Waterstone Consultancy
software | engineer | software.engineer@university.org | EngineeringCompany
electronics | engineer | electronics.engineer@university.org | EngineeringCompany
project | manager | project.manager@university.org | EngineeringCompany
Project | Sponsot | project.sponsor@company.com | Lloyds Bank

## DataValidation
Open
Scheduled
In progress
Done
Discarded

## Tasks
Deliverable | Task Name | Description | Who (Responsible) | Where | Comment
Case & Cables | Design Case Internals |  | designer.engineer@university.org
Case & Cables | Simulate Assembly |  | manufacturing.engineer@university.org
Case & Cables | Research Power Supply |  | manufacturing.engineer@university.org
Case & Cables | Design Case outside |  | designer.engineer@university.org
Case & Cables | Case Durability / FEA |  | manufacturing.engineer@university.org
Case & Cables | Research Raspberry Pi Alternatives |  | manufacturing.engineer@university.org
Case & Cables | Research Manufacturing Options |  | manufacturing.engineer@university.org
Loudspeaker | Select Loudspeaker |  | electronics.engineer@university.org
Loudspeaker | Market Analysis |  | electronics.engineer@university.org
Market Analysis | Carry out competitor analysis |  | project.manager@university.org
Market Analysis | Carry out a customer analysis |  | project.manager@university.org
Power Supply | Select Power Supply |  | electronics.engineer@university.org
Power Supply | Select Power Button |  | electronics.engineer@university.org
Power Supply | Select Volume Button |  | electronics.engineer@university.org
Power Supply | Research Power Supply |  | software.engineer@university.org
Power Supply | Research Power Button |  | software.engineer@university.org
Power Supply | Research Volume Button |  | software.engineer@university.org
Program Pi | Evaluate App Options |  | software.engineer@university.org
Program Pi | Research Plattforms |  | software.engineer@university.org
Program Pi | Connect to Raspberry Pi |  | electronics.engineer@university.org
Program Pi | Programm Raspberri Pi |  | software.engineer@university.org
Program Pi | Develop Use Cases |  | software.engineer@university.org
Project | Project Management |  | project.manager@university.org
Prototype | Present Concept |  | manufacturing.engineer@university.org
Prototype | Prepare Presentation |  | manufacturing.engineer@university.org
Prototype | Manufacturing Cost Analysis |  | manufacturing.engineer@university.org
Project | Software Development |  | project.manager@university.org
Project | Harware development |  | project.manager@university.org