## Gantt_Planned
Date | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | TASK TOTAL | SUB TOTAL
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | Contingency | Responsible | Contributor1 | Contributor2
Workload | 63 | 144 | 119 | 84 | 87 | 47 | 47 | 27 | 32 | 17 | 12 | 17 | 12 | 17 | 12 | 2 | 2 | 2 | 2 | 745 | 144
Project Management | [20 empty] | 104
Initiation | 10 | 10 | [17 empty] | 20 |  | Toby
Planning | 10 | 12 | 12 | 12 | [15 empty] | 46 |  | Toby
Monitoring | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 38 |  | Toby
Market Analysis | 10 | 10 | [17 empty] | 20 | 110
Competitor analysis |  | 5 | 15 | [16 empty] | 20
Customer analysis |  |  | 10 | 10 | [15 empty] | 20
Supplier analysis |  |  |  | 10 | 20 | [14 empty] | 30
Present Concept |  |  |  |  | 20 | [14 empty] | 20
Electronics | [19 empty] | 0 | 176
Decide Motor Charcteristics |  | 5 | [17 empty] | 5 |  | Sam | Jacob | Haydn
Research specific motors |  |  | 10 | 5 | [15 empty] | 15 |  | Sam | Jacob | Haydn
Research Battery | 5 | 5 | 10 | [16 empty] | 20 |  | Sam
Battery Controller |  |  |  | 15 | [15 empty] | 15 |  | Haydn
Control System | 5 | 5 | 5 | 10 | 5 | [14 empty] | 30 |  | Haydn | Sam
Regenerative Braking Research | 1 | 15 | 5 | [16 empty] | 21 |  | All
Feasability Report |  | 10 | 10 | 10 | 10 | [14 empty] | 40
User Interface |  |  |  |  | 10 | 10 | 10 | [12 empty] | 30
0
0
0
0
0
0
Mecanics | [19 empty] | 0 | 200
Gearing Requiremts | 5 | 10 | [17 empty] | 15 |  | Jacob
Transmission Implentation |  |  | 10 |  |  | 10 | [13 empty] | 20 |  | Jacob
Board Stress analysis | 5 | 10 | 10 | [16 empty] | 25 |  | Edward
Design Housing for elcronics ect |  |  |  |  | 10 | 15 | 15 | 5 | [11 empty] | 45 |  | Edward
Suspension Research | 5 | 10 | 10 | [16 empty] | 25 |  | Toby
Wheels | 5 | 10 | [17 empty] | 15 |  | Hugo
Bearings |  | 15 | [17 empty] | 15 |  | Hugo
Feasability Report |  | 10 | 10 | 10 | 10 | [14 empty] | 40 |  | All
0
Prototyping and Finalising | [19 empty] | 0 | 155
Prototype | [5 empty] | 10 | 20 | 20 | [11 empty] | 50 |  | All?
Prototype Troubleshooting | [8 empty] | 30 | 10 | [9 empty] | 40 |  | All?
Cost Analysis | [9 empty] | 5 | 10 | [8 empty] | 15 |  | All?
Large Scale Prodution Analysis | [11 empty] | 15 | [7 empty] | 15 |  | All?
Prepare Presentation | [12 empty] | 10 | 5 | [5 empty] | 15 |  | All?
Prepare Project Report | [13 empty] | 10 | 10 |  |  |  |  | 20 |  | All?
[20 empty] | 745 | 745

## Contacts
FirstName | FamilyName | Email | Organisation | Phone | Mobile | Address
Oliver | Vogt | oliver.vogt@university.org | EngineeringCompany
Designer | Engineer | designer.engineer@university.org | EngineeringCompany
Programmer | Engineer | programmer.engineer@university.org | EngineeringCompany
Manufacturing | Engineer | manufacturing.engineer@university.org | EngineeringCompany
Director | ToBeNamed | DirectorToBeNamed@university.org | EngineeringCompany
Marketing | ToBeNamed | MarketingToBeNamed@university.org | EngineeringCompany
Finance | ToBeNamed | FinanceToBeNamed@university.org | EngineeringCompany
Bank | ToBeNamed | BankToBeNamed@university.org | Lloyds Bank
S-Customer | standard | S-CustomerToBeNamed@university.org | Rapid Electonics
Adv-Customer | advanced | Adv-CustomerToBeNamed@university.org | Amazon
Retailer | ToBeNamed | RetailerToBeNamed@university.org | Carphone Warehouse
Wholesaler | ToBeNamed | WholesalerToBeNamed@university.org | Amazon
IT-Support | ToBeNamed | IT-SupportToBeNamed@university.org | Waterstone Consultancy
Design | Tutor1 | design.tutor1@university.org | Waterstone Consultancy
Design | Tutor2 | design.tutor2@university.org | Waterstone Consultancy
software | engineer | software.engineer@university.org | EngineeringCompany
electronics | engineer | electronics.engineer@university.org | EngineeringCompany
project | manager | project.manager@university.org | EngineeringCompany
Project | Sponsot | project.sponsor@company.com | Lloyds Bank